## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | DT ; 11/13/23 ; After login, you can see the Needs, but there is no specific 'Needs' page
Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page.
Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute.
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | DT ; 11/13/23 ;
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | DT; 11/13/23 ;
As a Developer I want to Submit a request to get a need from the need cupboard so that it is added to the funding basket. | Given I am a developer when submit a request to the rest api server then I am able to add a need from the needs cupboard to the funding basket. | Pass | DT ; 11/12/23 ;
| Given I am a developer when I try to create a need that is not also in the need cupboard then I get a 404 not found error. | Pass | DT ; 11/12/23 ;
| Given I am a developer when I try to create a need that already exists then I get a 409 conflict error. | Pass | DT ; 11/12/23 ;
As a Developer I want to Submit a request to get the funding basket so that I can view all the needs in the funding basket. | Given I am a developer when submit a get request to the server then I should receive the needs in the funding basket.
As a Developer I want to Submit a request to delete a need so that it is no longer in the funding basket. | Given I am a developer when I submit a request to delete a need in the funding basket then the need will be deleted.
Given I am a developer when I submit a request to delete a need in the funding basket then the need will be deleted.
As a manager I want to log in so that I can manage the needs cupboard. | Given I am an admin when I log in then I EXPECT to be able to add/delete/edit needs from the cupboard.
As a helper I want to search for a specific need so that I can narrow down the needs that I want to fund. | Given there is a search bar on screen when I type in a characters then I expect needs to come up below the bar. | Pass | DT ; 11/12/23 ;
| Given there is a search bar on screen when I type in a characters then I expect matching needs to pop up below. | Pass | DT ; 11/12/23 ;
As a manager I want to add to, remove from, and edit the needs cupboard so that the helpers can order the correct needs. | Given I am an admin when I click add Need a need to the database then I am able to add a need from the needs cupboard | Pass | DT ; 11/12/23 ;
| Given I am an admin when I click add the 'X' icon then I am able to delete a Need from the need cupboard. | Pass | DT ; 11/12/23 ;
| Given I am an admin when I click a need and edit its details then I am able to update that need within the need cupboard | Pass | DT ; 11/12/23 ;
SPRINT 3 STUFF:
None ready for testing yet.